## Welcome
Everything you need to plan a successful event from start to finish!
Event Planning Checklist |  | Welcome to the ultimate event planning checklist! This checklist details essential event tasks in chronological order, starting nine months before your event begins and ending after your event is complete. How to use this template This planning checklist is meant to be customizable! We've given you a solid foundation, but feel free to add and remove as needed! |  |  |  | `
Use the buttons below to easily navigate to each section of the checklist.
|  | 6-7 months before | 4-6 months before | 3 months before | 1-2 months before
|  | 1 week before | During event | After event
| • | Use the tab feature to quickly easily navigate between stages of the event planning process.
| • | Use the due date column to add a target date for completing tasks and easily stay on track.
| • | Use the complete feature to cross off items as you finish them.
| • | Use the assignee column to easily delegate tasks to your team members.
Additional resources
How to use an event budget template
Event management process: 5 steps and stages to launching an event
Time management tips every event planner should know
Copyright © Webex Events (formerly Socio) 2022

## 6-7 months before
6-9 months before your event
| Task | Comments | Assignee | Due date | Complete?
Establish event goals
Target audience
Key objectives
Key messaging
| KPIs | How will you measure event success? Check out this guide on event marketing KPIs for inspiration.
Decide on the main event details
Event theme
Event format (in-person, virtual, or hybrid)
Estimate attendee count
Event date
| Event time & duration | Tip: Hosting a hybrid or virutal event? Be sure to include the event time zone(s) for easier planning!
Event location & venue
Brainstorm speakers, entertainers, etc.
| Work out the logistics | Tip: Some logistical items may be included with your venue rental. Always check before purchasing separately.
Hotel blocks
Transportation services
Tables, chairs, and lounge areas
A/V production
WiFi
Permits & contracts
Liability insurance
Security
Medical assistance / EMTs
Food & beverage service
Accessibility
Design/printing services
| Organize your finances | Need help getting started? Check out our free event budget template.
Determine ticket/pricing strategy
Create an event budget & estimate cost
Begin securing sponsorships
Create a contingency plan

## 4-6 months before
4-6 months before your event
| Task | Comments | Assignee | Due date | Complete?
Finalize main contracts & begin outreach
Finalize main contracts (venue, hotel, vendors, etc.)
Plan entertainment and begin reaching out to secure contracts
| Create list of potential speakers and begin reaching out to secure contracts | Include speakers for keynote sessions, panel talks, workshops, etc.
Secure event technology
Registration
Check-in & badge printing
Event platform (for in-person and hybrid events)
Mobile event app
A/V production equipment & staff
WiFi
Finalize event marketing plan
Finalize theme and branding
Build event website
| Launch and promote registration page | For in-person and hybrid events, it's best to launch and promote your registration page around the 4 month mark. For virtual events, you should aim to launch at least 1-2 months before, depending on their size and complexity.
Design and marketing materials (banners, signs, flyers, staff)
| Create and execute content marketing plan | Plan for blogs, email promotion, social media promotion, etc. and begin promotion.
Other
Design event swag
Release early-bird ticketing

## 3 months before
3 months before your event
| Task | Comments | Assignee | Due date | Complete?
Finalize entertainment contracts
Arrange lodging & transportation
Finalize speaker contracts
Arrange lodging & transportation
Get bio information and headshots
Finalize photographer contracts
Arrange lodging & transportation
Finalize sponsorships
Update event budget with sponsorship funds
| Create run of show document | Check out our free hybrid run of show template to get started!
Add keynote sessions
Add workshops/breakout sessions
Add panel interviews
Add event activities and entertainment
Add lunch & beverage breaks
Order event materials and decor
Printed materials/signage
Staff shirts, badges, etc.
Swag
Misc. decor

## 1-2 months before
1-2 months before your event
| Task | Comments | Assignee | Due date | Complete?
2 months before
Get speakers/sponsors involved in marketing your event
Confirm contracts
Ramp up event promotion
1 month before
Send out final confirmations and reminders
Finalize seating charts and event layout
Finalize A/V production
Finalize food & beverage order
Finalize contingency plans
Make agenda updates if necessary
| Test your event tech | Whether you're doing an in-person, virtual, or hybrid event, it's important to test your event tech to ensure everythign is running as smoothly as possible.

## 1 week before
The week before your event
| Task | Comments | Assignee | Due date | Complete?
5-7 days before
Check over previous list items and make sure they are on track
Update run of show
Update agenda (if necessary)
Finalize contingency plans
3-5 days before
Confirm BEOs and F&B numbers
Meet with event team and provide internal agenda
Hold a team meeting with all internal team members attending the event to align and provide an opportunity to ask questions
1-2 days before
| Test your event tech... again | Whether you're doing an in-person, virtual, or hybrid event, it's important to test your event tech to ensure everythign is running as smoothly as possible.
Confirm signage is in place at the venue
Confirm tables and decor, and ensure the place cards and table numbers are in place at the venue
Check that accessible areas are working and operational (bathroom, outdoor ramps, stair railings)

## During event
During the event
| Task | Comments | Assignee | Due date | Complete?
Promote, promote, promote!
| Share live coverage social media | Tip: Even if it's too late for same-day registration, this content will create a buzz for your next event!
| Check in with your photographer(s) | Tip: See something you want captured? Check in with your photographers during the even to let them know!
Final preparations
Walk through your internal event agenda with committee leads
Meet up with the vendors and provide them access
Prepare the venue green room with food and beverages for presenters and entertainers
| Review your event data and make any necessary improvements | Tip: When vetting event tech, make sure the event management platform you choose offers data and reporting.
Session attendees
Engagement metrics
Speaker performance
Session drop-off (virutal)

## After event
After the event
| Task | Comments | Assignee | Due date | Complete?
Get feedback
Review event platform data
Send post-event surveys to sponsors and attendees
Meet with your team to evaluate the successes and misses
Send sponsors focused data on their campaigns and thank them for their involvement
Send thank you letters/emails to sponsors, attendees, media, speakers, team members, and volunteers
Share event highlights with attendees, speakers, and sponsors via email
Post event highlights on social media
Set up a post-event community
Repurpose event content
Use session transcripts to create blog content
Create video cutdowns to share on social and re-use for future events